## Sheet1
Task | Subtask |  |  |  |  | Person (time allocated)
UI
| Design |  |  |  |  | AM (20h)
| Implementation |  |  |  |  | AM, MM (40h)
| Optimization |  |  |  |  | AM, MM (15h)
Databases
| API Implementation |  |  |  |  | AM, MM (40h)
| Data Collection/Selection |  |  |  |  | MM, MT (45h)
Data Visualization
| GIS Maps |  |  |  |  | MM (20h)
| Charts and Graphs |  |  |  |  | AM, MM (20h)
| Exportable Spreadsheets |  |  |  |  | MM (5h)
Algorithm
| Initial Design (Data Cleaning, Analysis, Prediction) |  |  |  |  | AM, MM, MT (120h)
| Refinement (Speed) |  |  |  |  | MT (80h)
| Refinement (Modularity) |  |  |  |  | AM, MT (40h)
Management and Documentation
| SPMP |  |  |  |  | AM, MM, MT(10h)
| RAS |  |  |  |  | AM, MM, MT (25h)
| SDD |  |  |  |  | AM, MM, MT (10h)
Testing
| Defect Resolution |  |  |  |  | AM, MM, MT (40h)
| Verification and Validation |  |  |  |  | AM, MM, MT (20h)
Overall Hours
Anish Malhotra |  |  |  | 175h
Chun Zen Marc Tse |  |  |  | 185h
Mehmed Mladenov |  |  |  | 180h
Cumulative |  |  |  | 540h
Task | [5 empty] | Skill Level Required (1 low - 5 high)
UI
| Design |  |  |  |  | 1
| Implementation |  |  |  |  | 2
| Optimization |  |  |  |  | 1
Database
| API Implementation |  |  |  |  | 3
| Data Collection/Selection |  |  |  |  | 3
Data Visualization
| GIS Maps |  |  |  |  | 4
| Charts and Graphs |  |  |  |  | 3
| Exportable Spreadsheets |  |  |  |  | 2
Algorithm
| Initial Design (Data Cleaning, Analysis, Prediction) |  |  |  |  | 5
| Refinement (Speed) |  |  |  |  | 5
| Refinement (Modularity) |  |  |  |  | 3
Management and Documentation
| SPMP |  |  |  |  | 1
| RAS |  |  |  |  | 1
| SDD |  |  |  |  | 1
Testing
| Defect Resolution |  |  |  |  | 3
| Verification and Validation |  |  |  |  | 3
Work Breakdown Structure (person-weeks)
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
AM
MM
MT

## Sheet2
Work Breakdown Structure (person-weeks)
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
AM | bar: Month 1 1 to Month 4 4
MM | bar: Month 1 1 to Month 4 4
MT | bar: Month 1 1 to Month 4 4
Weekly Totals |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Cumulative |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48

## Sheet3
Milestones | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project Proposal | bar: February 1
Project Proposal - Complete | bar: February 2
RAS - Business Defintion | bar: February 2 to February 3
RAS - Software Requirements | bar: February 4 to March 1
RAS - Complete | bar: April 1 to April 2
SPMP | bar: March 4 to April 1
SDD | bar: April 3 to April 4